## All Issues
Key | Summary | Type | Status | Priority | Assignee | Reporter | Created | Updated | Resolved | Labels | Parent | Comments #
AIP-10 | Data Indicator - Train | Task | Done | Medium | Nadine Kirnbauer | Akhil Elango | 2026-01-27 14:22 | 2026-01-27 14:27 | 2026-01-27 14:26 |  |  | 0
AIP-100 | Refactor handling of static files in the data handler | Task | Done | Medium | Nadine Kirnbauer | Michal Bronicki | 2026-03-12 16:04 | 2026-03-31 16:42 | 2026-03-31 16:42 |  | AIP-62 | 0
AIP-101 | Refactor cronjobs for data handler | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Michal Bronicki | 2026-03-12 16:05 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-40 | 0
AIP-103 | Implement periodic data aggregation for live data | Task | Done | Medium | Rakesh Lakshmanan | Michal Bronicki | 2026-03-12 16:07 | 2026-03-31 16:42 | 2026-03-31 16:42 |  | AIP-62 | 0
AIP-106 | Forget password functionality | Subtask | Done | Medium |  | Michal Bronicki | 2026-03-12 16:33 | 2026-03-19 15:22 | 2026-03-19 15:22 |  | AIP-99 | 0
AIP-107 | Fix security issue in the notification controller | Bug | Done | Low |  | Michal Bronicki | 2026-03-12 18:22 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-75 | 0
AIP-108 | Refactor cycle API to geojson | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Stevin Joseph Sebastian Stevin Joseph Sebastian | 2026-03-19 18:34 | 2026-03-19 19:15 | 2026-03-19 19:15 |  | AIP-62 | 0
AIP-109 | Refactor Bus Static Data source from CSV to API | Task | Done | Medium |  | Stevin Joseph Sebastian Stevin Joseph Sebastian | 2026-03-19 18:34 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-62 | 0
AIP-11 | Fix CI pipeline | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-01-27 15:04 | 2026-01-27 17:19 | 2026-01-27 15:05 | DEVOPS |  | 0
AIP-112 | Implement offline mode with persistent data caching | Task | Done | Medium | Naman | Naman | 2026-03-22 18:27 | 2026-04-10 17:17 | 2026-04-10 17:17 |  |  | 2
AIP-113 | TRAFFIC-1: Display Traffic Diversion Recommendations | Task | Done | High | Ioannis Christofilogiannis | Naman | 2026-03-23 00:08 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-58 | 0
AIP-114 | CYCLE-1: Demand Analysis Dashboard | Task | Done | Medium | Rakesh Lakshmanan | Naman | 2026-03-23 00:09 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-62 | 0
AIP-115 | CYCLE-2: Full or Empty Station Alerts | Task | Done | High | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:09 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-58 | 0
AIP-116 | CYCLE-3: Detect Areas with Low Cycle Access | Task | Done | Medium | Rakesh Lakshmanan | Naman | 2026-03-23 00:09 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-62 | 0
AIP-117 | CYCLE-4: Add or Remove Bicycles Simulation | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:09 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-56 | 0
AIP-118 | CYCLE-5: Simulate Effect of Station Changes | Task | Done | Medium | Rakesh Lakshmanan | Naman | 2026-03-23 00:09 | 2026-04-10 17:17 | 2026-04-10 17:17 |  | AIP-56 | 0
AIP-119 | CYCLE-6: Cycle Module Documentation | Task | Done | Low | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:09 | 2026-04-10 17:16 | 2026-04-10 17:16 |  | AIP-57 | 0
AIP-12 | Fix frontend Dockerfile | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-01-27 15:05 | 2026-01-27 17:19 | 2026-01-27 15:05 | DEVOPS |  | 0
AIP-120 | BUS-1: Common Bus Delays Dashboard | Task | Done | High | Mukul Ghare | Naman | 2026-03-23 00:10 | 2026-04-02 15:18 | 2026-04-02 15:18 |  | AIP-62 | 0
AIP-121 | BUS-2: Display Bus Delays Based on Events/Construction | Task | Done | High | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:10 | 2026-04-10 17:16 | 2026-04-10 17:16 |  | AIP-61 | 0
AIP-122 | BUS-3: Suggest Alternative Transport During Disruption | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:10 | 2026-04-10 17:16 | 2026-04-10 17:16 |  | AIP-61 | 0
AIP-123 | BUS-4: Bus Frequency Analysis | Task | Done | Medium | Michal Bronicki | Naman | 2026-03-23 00:10 | 2026-04-10 17:16 | 2026-04-10 17:16 |  | AIP-62 | 0
AIP-124 | BUS-5: Bus Route Simulation | Task | Done | Low | Michal Bronicki | Naman | 2026-03-23 00:10 | 2026-04-10 17:16 | 2026-04-10 17:15 |  | AIP-56 | 0
AIP-125 | TRAIN-1: Display Common Train Delays | Task | Done | High | Naman | Naman | 2026-03-23 00:10 | 2026-03-25 13:27 | 2026-03-25 13:27 |  | AIP-62 | 0
AIP-126 | TRAIN-2: Train Delays Based on Events/Construction | Task | Done | High | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:19 | 2026-04-10 17:16 | 2026-04-10 17:15 |  | AIP-61 | 0
AIP-127 | TRAIN-3: Train Under/Over Utilisation Analysis | Task | Done | Medium | Naman | Naman | 2026-03-23 00:19 | 2026-03-31 16:51 | 2026-03-31 16:51 |  | AIP-75 | 0
AIP-128 | TRAIN-4: Alternative Transport for Train Disruptions | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:19 | 2026-04-10 17:16 | 2026-04-10 17:15 |  | AIP-61 | 0
AIP-129 | TRAIN-5: Train Frequency Recommendations | Task | Done | Medium | Naman | Naman | 2026-03-23 00:19 | 2026-03-31 16:51 | 2026-03-31 16:51 |  | AIP-55 | 0
AIP-13 | Bus indicator in data handler | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-01-27 15:11 | 2026-02-17 16:44 | 2026-02-05 17:12 | DATAHANDLER | AIP-62 | 0
AIP-130 | TRAIN-6: Train Simulation | Task | Done | Low | Akhil Elango | Naman | 2026-03-23 00:19 | 2026-04-10 17:16 | 2026-04-10 17:15 |  | AIP-56 | 0
AIP-131 | LUAS-1: Display Common Tram Delays | Task | Done | High | Sudesh Muralidharan | Naman | 2026-03-23 00:20 | 2026-04-10 17:16 | 2026-04-10 17:15 |  | AIP-62 | 0
AIP-132 | LUAS-2: Tram Delays Based on Events/Construction | Task | Done | High | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:20 | 2026-04-10 17:16 | 2026-04-10 17:15 |  | AIP-61 | 0
AIP-134 | LUAS-3: Tram Under/Over Utilisation Analysis | Task | Done | Medium | Sudesh Muralidharan | Naman | 2026-03-23 00:20 | 2026-04-10 17:14 | 2026-04-10 17:14 |  | AIP-62 | 0
AIP-135 | LUAS-4: Alternative Transport for Tram Disruptions | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:20 | 2026-04-10 17:14 | 2026-04-10 17:14 |  | AIP-61 | 0
AIP-136 | LUAS-5: Tram Frequency Recommendations | Task | Done | Medium | Sudesh Muralidharan | Naman | 2026-03-23 00:21 | 2026-04-10 17:14 | 2026-04-10 17:14 |  | AIP-55 | 0
AIP-137 | LUAS-6: Tram Simulation | Task | Done | Low | Nadine Kirnbauer | Naman | 2026-03-23 00:21 | 2026-04-10 17:14 | 2026-04-10 17:14 |  | AIP-56 | 0
AIP-138 | MISC-1: Display Events on Map | Task | Done | High | Ioannis Christofilogiannis | Naman | 2026-03-23 00:21 | 2026-03-31 01:40 | 2026-03-31 01:40 |  | AIP-57 | 0
AIP-139 | MISC-2: Live Disruption Detection | Task | Done | High | Stevin Joseph Sebastian Stevin Joseph Sebastian | Naman | 2026-03-23 00:29 | 2026-04-10 17:13 | 2026-04-10 17:13 |  | AIP-61 | 0
AIP-14 | Pedestrians indicator in data handler | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-01-27 15:13 | 2026-02-17 16:44 | 2026-02-10 13:27 | DATAHANDLER | AIP-62 | 0
AIP-140 | MISC-3: Live Pedestrian Data | Task | Done | Medium | Ioannis Christofilogiannis | Naman | 2026-03-23 00:29 | 2026-03-31 01:40 | 2026-03-31 01:40 |  | AIP-58 | 0
AIP-141 | OFFLINE-1: Implement Progressive Web App (PWA) with Offline Support | Task | Done | High | Naman | Naman | 2026-03-23 00:30 | 2026-04-10 17:13 | 2026-04-10 17:13 |  | AIP-75 | 0
AIP-142 | APPROVAL-1: Stakeholder Demo & Approval Process | Task | Done | High | Akhil Elango | Naman | 2026-03-23 00:30 | 2026-04-10 17:13 | 2026-04-10 17:13 |  | AIP-57 | 0
AIP-143 | UI-1: Overview Dashboard & Login Page Polish | Task | Done | Medium | Mohammad Owais Khan | Naman | 2026-03-23 00:30 | 2026-04-10 17:13 | 2026-04-10 17:13 |  | AIP-57 | 0
AIP-144 | Add AWS SES secrets in production env | Task | Done | Medium | Mukul Ghare | Mukul Ghare | 2026-03-30 17:04 | 2026-04-10 17:13 | 2026-04-10 17:13 |  | AIP-40 | 0
AIP-145 | LUAS-1 Display live luas data | Task | Done | Medium | Sudesh Muralidharan | Sudesh Muralidharan | 2026-03-31 16:53 | 2026-03-31 16:53 | 2026-03-31 16:53 |  |  | 0
AIP-146 | LUAS-2 Display live luas delay | Task | Done | Medium | Sudesh Muralidharan | Sudesh Muralidharan | 2026-03-31 16:53 | 2026-03-31 16:53 | 2026-03-31 16:53 |  |  | 0
AIP-15 | Car indicator in data handler | Task | Done | Medium | Mohammad Owais Khan | Michal Bronicki | 2026-01-27 15:15 | 2026-02-17 16:51 | 2026-02-11 20:02 | DATAHANDLER | AIP-62 | 0
AIP-16 | Construction indicator in data handler | Task | Done | Medium | Mohammad Owais Khan | Michal Bronicki | 2026-01-27 15:15 | 2026-02-17 16:51 | 2026-02-17 16:40 | DATAHANDLER | AIP-62 | 0
AIP-17 | Cycle indicator in data handler | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Michal Bronicki | 2026-01-27 15:16 | 2026-02-19 17:36 | 2026-02-19 17:36 | DATAHANDLER | AIP-62 | 0
AIP-18 | Events indicator in data handler | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Michal Bronicki | 2026-01-27 15:16 | 2026-03-04 15:56 | 2026-03-04 15:56 | DATAHANDLER | AIP-62 | 0
AIP-19 | Train indicator in data handler | Task | Done | Medium | Sudesh Muralidharan | Michal Bronicki | 2026-01-27 15:17 | 2026-02-27 15:51 | 2026-02-27 15:51 | DATAHANDLER | AIP-62 | 0
AIP-20 | Tram indicator in data handler | Task | Done | Medium | Sudesh Muralidharan | Michal Bronicki | 2026-01-27 15:17 | 2026-02-27 15:51 | 2026-02-27 15:51 | DATAHANDLER | AIP-62 | 0
AIP-22 | Data Indicator - Bus | Task | Done | Medium | Mukul Ghare | Akhil Elango | 2026-01-27 16:43 | 2026-01-27 16:47 | 2026-01-27 16:43 |  |  | 0
AIP-23 | Data Indicator - Cycle | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Akhil Elango | 2026-01-27 16:44 | 2026-01-27 16:48 | 2026-01-27 16:45 |  |  | 0
AIP-24 | Data Indicator - Car and Electric Vehicles. | Task | Done | Medium | Akhil Elango | Akhil Elango | 2026-01-27 16:46 | 2026-01-27 16:47 | 2026-01-27 16:46 |  |  | 0
AIP-25 | Data Indicator - Event | Task | Done | Medium | Rakesh Lakshmanan | Akhil Elango | 2026-01-27 16:48 | 2026-01-27 16:49 | 2026-01-27 16:49 |  |  | 0
AIP-26 | Resolve python vulnerability alerts reported by github | Task | Done | Low |  | Michal Bronicki | 2026-01-27 17:15 | 2026-04-10 17:19 | 2026-04-10 17:19 | DATAHANDLER, INFERENCEENGINE |  | 0
AIP-27 | Add deployment pipeline | Task | Done | Medium | Naman | Akhil Elango | 2026-01-27 17:23 | 2026-02-17 16:48 | 2026-02-06 18:17 | DEVOPS | AIP-40 | 0
AIP-28 | Fix linter errors in data handler | Task | Done | Low | Mohammad Owais Khan | Akhil Elango | 2026-01-27 17:24 | 2026-03-19 17:30 | 2026-03-19 17:30 | DATAHANDLER | AIP-62 | 0
AIP-29 | Fix linter errors in frontend | Task | Done | Medium |  | Akhil Elango | 2026-01-27 17:25 | 2026-04-10 17:19 | 2026-04-10 17:19 | FRONTEND |  | 0
AIP-30 | Fix static analysis errors in Hermes | Task | Done | Medium |  | Akhil Elango | 2026-01-27 17:26 | 2026-04-10 17:19 | 2026-04-10 17:19 | HERMES |  | 0
AIP-32 | Manual deployment of GKE cluster | Task | Done | High | Naman | Akhil Elango | 2026-01-27 17:28 | 2026-02-17 16:48 | 2026-01-30 23:02 | DEVOPS | AIP-40 | 3
AIP-33 | Start the ML model development - With placeholder inputs | Task | Done | Medium | Akhil Elango | Ioannis Christofilogiannis | 2026-01-27 17:33 | 2026-02-17 16:45 | 2026-02-06 18:35 |  | AIP-55 | 1
AIP-34 | Static bus data in data handler | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-01-29 13:43 | 2026-02-17 16:46 | 2026-01-29 15:04 | DATAHANDLER | AIP-62 | 0
AIP-35 | Examine why time entries with hours > 24 are present in the GTFS stop_times data | Bug | Done | Medium |  | Michal Bronicki | 2026-01-29 14:07 | 2026-04-10 17:19 | 2026-04-10 17:19 | DATAHANDLER |  | 0
AIP-36 | Initial Implementation of Recommendation Model | Task | Done | Medium | Akhil Elango | Akhil Elango | 2026-01-29 14:39 | 2026-02-17 16:46 | 2026-02-03 17:24 |  | AIP-55 | 0
AIP-37 | Test-first Implementation of Simulation Model | Task | Done | Medium | Ioannis Christofilogiannis | Akhil Elango | 2026-01-29 14:41 | 2026-02-17 16:55 | 2026-02-17 16:55 |  | AIP-56 | 1
AIP-38 | Refactor | Subtask | Done | Medium |  | Ioannis Christofilogiannis | 2026-01-29 15:55 | 2026-04-10 17:19 | 2026-04-10 17:19 |  | AIP-37 | 0
AIP-39 | Keycloak Changes | Task | Done | Medium | Mukul Ghare | Rakesh Lakshmanan | 2026-01-30 17:19 | 2026-02-19 18:11 | 2026-02-19 18:11 |  | AIP-75 | 0
AIP-4 | Data Indicator - Pedestrian | Task | Done |  | Naman | Akhil Elango | 2026-01-27 13:54 | 2026-01-27 15:09 | 2026-01-27 14:11 |  |  | 0
AIP-40 | Infra | Epic | Done | Medium | Naman | Naman | 2026-01-30 23:10 | 2026-04-10 17:19 | 2026-04-10 17:19 | DEVOPS |  | 0
AIP-41 | Bind dev.citycontrol.me and enable HTTPS | Task | Done | Medium |  | Naman | 2026-01-30 23:13 | 2026-02-03 13:42 | 2026-02-03 13:42 |  | AIP-40 | 0
AIP-42 | Harden NetworkPolicies (least-privilege networking) | Task | Done | Medium | Naman | Naman | 2026-01-30 23:20 | 2026-02-13 17:00 | 2026-02-13 17:00 |  | AIP-40 | 1
AIP-43 | Terraform infrastructure for dev | Task | Done | Medium | Michal Bronicki | Naman | 2026-01-30 23:21 | 2026-03-02 14:33 | 2026-03-02 14:33 |  | AIP-40 | 0
AIP-44 | Implement mTLS for internal services | Task | Done | Medium | Naman | Naman | 2026-01-30 23:22 | 2026-02-13 17:00 | 2026-02-13 17:00 |  | AIP-40 | 0
AIP-45 | Simulation Documentation - For followup implementation | Task | Done | Medium | Ioannis Christofilogiannis | Ioannis Christofilogiannis | 2026-02-03 14:19 | 2026-02-17 16:49 | 2026-02-10 13:27 |  | AIP-56 | 0
AIP-46 | Set up testing for data handler | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-02-03 15:09 | 2026-02-17 16:49 | 2026-02-05 16:30 | DATAHANDLER | AIP-62 | 0
AIP-47 | Testing Cycle Data Handler | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Stevin Joseph Sebastian Stevin Joseph Sebastian | 2026-02-03 18:19 | 2026-02-19 17:36 | 2026-02-19 17:36 | TESTING | AIP-62 | 0
AIP-50 | Testing Tram Data Handler | Task | Done | Medium | Sudesh Muralidharan | Sudesh Muralidharan | 2026-02-06 17:28 | 2026-02-27 15:51 | 2026-02-27 15:51 | TESTING | AIP-62 | 0
AIP-51 | Testing Train Data Handler | Task | Done | Medium | Sudesh Muralidharan | Sudesh Muralidharan | 2026-02-06 17:29 | 2026-02-27 15:51 | 2026-02-27 15:51 | TESTING | AIP-62 | 0
AIP-53 | Testing Keycloack Changes | Task | Done | Medium | Naman | Stevin Joseph Sebastian Stevin Joseph Sebastian | 2026-02-06 18:19 | 2026-03-04 13:32 | 2026-03-04 13:32 | TESTING | AIP-75 | 0
AIP-54 | Construction and Traffic updates data handler | Task | Done | Medium | Ioannis Christofilogiannis | Ioannis Christofilogiannis | 2026-02-06 18:40 | 2026-02-17 16:44 | 2026-02-06 18:40 |  | AIP-62 | 0
AIP-55 | Machine Learning | Epic | Done | Medium |  | Akhil Elango | 2026-02-06 18:42 | 2026-04-10 17:19 | 2026-04-10 17:19 |  |  | 0
AIP-56 | Simulation | Epic | Done | Medium |  | Akhil Elango | 2026-02-06 18:43 | 2026-04-10 17:19 | 2026-04-10 17:19 |  |  | 0
AIP-57 | Frontend | Epic | Done | Medium |  | Akhil Elango | 2026-02-06 18:43 | 2026-04-10 17:19 | 2026-04-10 17:19 |  |  | 0
AIP-58 | API Integration for indicators | Epic | Done | Medium |  | Akhil Elango | 2026-02-06 18:44 | 2026-04-10 17:19 | 2026-04-10 17:19 |  |  | 0
AIP-59 | EV Charging Statistics Model | Task | Done | Medium | Akhil Elango | Akhil Elango | 2026-02-06 18:52 | 2026-02-17 13:20 | 2026-02-17 13:19 |  | AIP-55 | 0
AIP-61 | Disruption | Epic | Done | Medium |  | Akhil Elango | 2026-02-06 18:54 | 2026-04-10 17:19 | 2026-04-10 17:19 |  |  | 0
AIP-62 | Data Handler | Epic | Done | Medium |  | Akhil Elango | 2026-02-06 18:56 | 2026-04-10 17:19 | 2026-04-10 17:19 |  |  | 0
AIP-63 | Bus indicator integration with frontend | Task | Done | Medium | Akhil Elango | Akhil Elango | 2026-02-06 18:58 | 2026-03-04 13:32 | 2026-03-04 13:32 |  | AIP-58 | 0
AIP-64 | Cycle Indicator integration with frontend | Task | Done | Medium | Rakesh Lakshmanan | Akhil Elango | 2026-02-06 19:00 | 2026-03-24 13:44 | 2026-03-24 13:44 |  | AIP-58 | 0
AIP-65 | Notification integration with frontend | Task | Done | Medium | Mukul Ghare | Akhil Elango | 2026-02-06 19:02 | 2026-02-19 16:42 | 2026-02-19 16:42 |  | AIP-58 | 0
AIP-66 | Pollution Estimation | Task | Done | Medium | Akhil Elango | Akhil Elango | 2026-02-08 12:13 | 2026-03-23 15:17 | 2026-03-23 15:17 |  | AIP-75 | 0
AIP-67 | Verify the implementation of TII construction/congestion data handler and add tests | Task | Done | Medium | Ioannis Christofilogiannis | Michal Bronicki | 2026-02-09 14:49 | 2026-03-04 13:31 | 2026-03-04 13:31 | DATAHANDLER | AIP-62 | 0
AIP-68 | Testing Events Data Handler | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Stevin Joseph Sebastian Stevin Joseph Sebastian | 2026-02-10 02:00 | 2026-03-04 15:56 | 2026-03-04 15:56 | TESTING | AIP-62 | 0
AIP-69 | Implement comprehensive entrypoints for the data handler | Task | Done | Medium | Stevin Joseph Sebastian Stevin Joseph Sebastian | Michal Bronicki | 2026-02-10 13:41 | 2026-03-31 16:42 | 2026-03-31 16:42 | DATAHANDLER | AIP-62 | 0
AIP-7 | Remove Loki | Task | Done | Medium | Rakesh Lakshmanan | Rakesh Lakshmanan | 2026-01-27 14:16 | 2026-02-17 16:48 | 2026-02-06 18:17 | HERMES | AIP-75 | 0
AIP-70 | Fix SQL enum schema issues in data handler | Bug | Done | High | Michal Bronicki | Michal Bronicki | 2026-02-10 13:47 | 2026-02-17 16:51 | 2026-02-10 14:14 |  | AIP-62 | 0
AIP-71 | Tests for car data handler | Task | Done | Medium | Mohammad Owais Khan | Michal Bronicki | 2026-02-11 20:02 | 2026-02-17 16:51 | 2026-02-13 18:27 | DATAHANDLER | AIP-62 | 0
AIP-72 | Add pytest code coverage to CI pipeline | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-02-12 18:29 | 2026-02-17 16:53 | 2026-02-13 17:17 | DEVOPS | AIP-40 | 0
AIP-73 | Implement synthetic bus passenger count in data handler | Subtask | Done | Medium |  | Stevin Joseph Sebastian Stevin Joseph Sebastian | 2026-02-13 17:06 | 2026-04-10 17:18 | 2026-04-10 17:18 |  | AIP-63 | 0
AIP-74 | Hermes has no health probes | Bug | Done | Low |  | Naman | 2026-02-16 02:48 | 2026-04-10 17:18 | 2026-04-10 17:18 |  |  | 0
AIP-75 | Hermes | Epic | Done | Medium |  | Naman | 2026-02-17 16:48 | 2026-04-10 17:18 | 2026-04-10 17:18 |  |  | 0
AIP-76 | Testing of Construction Data Handler | Task | Done | Medium | Ioannis Christofilogiannis | Akhil Elango | 2026-02-17 17:01 | 2026-03-04 13:31 | 2026-03-04 13:31 |  | AIP-62 | 0
AIP-79 | EV Charging Points Model - Linear Regression Model for Predicting increase in EV | Task | Done | Medium | Naman | Akhil Elango | 2026-02-17 17:18 | 2026-03-12 16:01 | 2026-03-12 16:01 |  | AIP-55 | 0
AIP-8 | Data Indicator - Tram | Task | Done | Medium | Sudesh Muralidharan | Akhil Elango | 2026-01-27 14:16 | 2026-01-27 14:20 | 2026-01-27 14:19 |  |  | 0
AIP-80 | EV Charging Points Model - Design Output i.e. Data to send to Hermes. | Task | Done | Medium | Naman | Akhil Elango | 2026-02-17 17:18 | 2026-03-31 16:42 | 2026-03-31 16:42 |  | AIP-55 | 0
AIP-81 | EV Charging Points Model - Integrate Frontend and Backend | Subtask | Done | Medium |  | Akhil Elango | 2026-02-17 17:20 | 2026-03-31 16:44 | 2026-03-31 16:44 |  | AIP-80 | 0
AIP-82 | User Management - Integrate Frontend to "Add User" | Task | Done | Medium | Mukul Ghare | Akhil Elango | 2026-02-17 17:26 | 2026-03-04 13:32 | 2026-03-04 13:32 |  | AIP-57 | 0
AIP-83 | User Management - Role based access control for Users | Task | Done | Medium | Ioannis Christofilogiannis | Akhil Elango | 2026-02-17 17:27 | 2026-03-23 15:19 | 2026-03-23 15:19 |  | AIP-75 | 0
AIP-84 | Add ESLint rule for unsafe JSON parsing | Task | Done | High | Michal Bronicki | Michal Bronicki | 2026-02-19 12:58 | 2026-02-19 15:11 | 2026-02-19 15:11 |  | AIP-57 | 0
AIP-85 | EV Charging Points Model - Send the Heatmap and the prediction to the frontend | Task | Done | Medium | Naman | Akhil Elango | 2026-02-19 13:21 | 2026-03-31 16:42 | 2026-03-31 16:42 |  | AIP-55 | 0
AIP-87 | Notification integration with DB | Task | Done | Medium | Mohammad Owais Khan | Mukul Ghare | 2026-02-24 13:38 | 2026-03-19 15:33 | 2026-03-19 15:33 |  | AIP-75 | 0
AIP-88 | Add additional linter rules in data handler | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-02-27 15:43 | 2026-02-27 15:51 | 2026-02-27 15:51 |  | AIP-62 | 0
AIP-89 | Population raw data ingestion for ML | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-03-02 14:51 | 2026-03-04 15:46 | 2026-03-04 15:46 |  | AIP-62 | 0
AIP-9 | Fix static analysis bugs in hermes | Task | Done | Medium | Rakesh Lakshmanan | Rakesh Lakshmanan | 2026-01-27 14:17 | 2026-02-17 16:48 | 2026-02-03 13:22 | HERMES | AIP-75 | 0
AIP-90 | Public amenities raw data ingestion for ML | Task | Done | Medium | Michal Bronicki | Michal Bronicki | 2026-03-02 14:51 | 2026-03-11 15:03 | 2026-03-11 15:03 |  | AIP-62 | 0
AIP-91 | Modify existing postgres infra setup to enable PostGIS extension | Task | Done | High | Michal Bronicki | Michal Bronicki | 2026-03-02 15:56 | 2026-03-04 13:32 | 2026-03-04 13:32 |  | AIP-40 | 0
AIP-92 | Refactor bus synthetic ridership implementation to use geospatial queries | Task | Done | Low |  | Michal Bronicki | 2026-03-04 12:49 | 2026-04-10 17:18 | 2026-04-10 17:18 |  | AIP-62 | 0
AIP-93 | Examine database structure and query patterns for external bus data to ensure that relevant indexes are in place | Task | Done | Medium |  | Michal Bronicki | 2026-03-04 12:55 | 2026-04-10 17:18 | 2026-04-10 17:18 |  | AIP-62 | 0
AIP-94 | Car Statistics Display - Fetch data from Backend, process the data and display it to the frontend. | Task | Done | Medium | Akhil Elango | Akhil Elango | 2026-03-04 13:46 | 2026-03-11 11:37 | 2026-03-11 11:37 |  | AIP-58 | 0
AIP-95 | Fix Password for First Time Login | Task | Done | Medium | Mukul Ghare | Mukul Ghare | 2026-03-04 14:56 | 2026-03-11 14:55 | 2026-03-11 14:55 |  | AIP-58 | 0
AIP-97 | Fix the car data handler | Task | Done | Medium | Mohammad Owais Khan | Mohammad Owais Khan | 2026-03-04 17:15 | 2026-03-12 15:13 | 2026-03-12 15:13 |  | AIP-62 | 0
AIP-98 | Add Update Profile and Reset Password | Task | Done | Medium | Mukul Ghare | Mukul Ghare | 2026-03-10 18:59 | 2026-03-11 14:55 | 2026-03-11 14:55 |  | AIP-58 | 0
AIP-99 | Update notification to send email to correct user | Task | Done | Medium | Mukul Ghare | Mukul Ghare | 2026-03-12 15:30 | 2026-03-19 15:22 | 2026-03-19 15:22 |  | AIP-75 | 0

## By Status
Status | Count | % of Total
Done | 125 | 100%
TOTAL | 125

## By Assignee
Assignee | Done | Total
Akhil Elango | 9 | 9
Ioannis Christofilogiannis | 9 | 9
Michal Bronicki | 16 | 16
Mohammad Owais Khan | 7 | 7
Mukul Ghare | 9 | 9
Nadine Kirnbauer | 3 | 3
Naman | 15 | 15
Rakesh Lakshmanan | 8 | 8
Stevin Joseph Sebastian Stevin Joseph Sebastian | 18 | 18
Sudesh Muralidharan | 10 | 10
Unassigned | 21 | 21

## By Type
Issue Type | Count | % of Total
Task | 109 | 87.2%
Epic | 8 | 6.4%
Bug | 4 | 3.2%
Subtask | 4 | 3.2%

## Timeline
Week | Issues Created
2026-W04 | 37
2026-W05 | 18
2026-W06 | 7
2026-W07 | 10
2026-W08 | 2
2026-W09 | 8
2026-W10 | 7
2026-W11 | 3
2026-W12 | 30
2026-W13 | 3

## Comments
Issue Key | Issue Summary | Comment Author | Comment Date | Comment
AIP-112 | Implement offline mode with persistent data caching | Naman | 2026-03-22 18:29 | Proposed Solution Phase 1: Backend - Consolidated API Endpoints Create optimized, consolidated API endpoints that return comprehensive data snapshots for each transport mode: New Consolidated Endpoints : GET /api/v1/offline/bus-snapshot - All bus data (live vehicles, KPIs, routes, metrics) GET /api/v1/offline/cycle-snapshot - All cycle data (stations, availability, metrics) GET /api/v1/offline/train-snapshot - All train data (live trains, service stats, KPIs) GET /api/v1/offline/car-snapshot
AIP-112 | Implement offline mode with persistent data caching | Ioannis Christofilogiannis | 2026-03-31 01:42 | Do you want help with that?
AIP-32 | Manual deployment of GKE cluster | Naman | 2026-01-30 23:04 | Deployed the latest changes and the service is up and running on https://104.155.3.1 /.
AIP-32 | Manual deployment of GKE cluster | Naman | 2026-01-30 23:07 | DNS resolution needs to be added, Keycloak has the user with the following password as of now. username:testuser password:smartEnoughCity
AIP-32 | Manual deployment of GKE cluster | Naman | 2026-01-30 23:07 | DNS to ip resolution is in place. The dev environment should be accessible via dev.citycontrol.me
AIP-33 | Start the ML model development - With placeholder inputs | Akhil Elango | 2026-02-06 18:37 | this will be converted to a story in the upcoming sprints. The initial research is done on this.
AIP-37 | Test-first Implementation of Simulation Model | Akhil Elango | 2026-02-06 18:38 | This also has dependencies attached to it and will be made to a story which will e picked up in upcoming sprints
AIP-42 | Harden NetworkPolicies (least-privilege networking) | Naman | 2026-02-06 16:46 | Namespace-level baseline policies default-deny-all Deny all ingress + egress for all pods by default. allow-dns-egress Allow egress to kube-dns/CoreDNS on TCP/UDP 53 (usually in kube-system). allow-https-egress Allow egress to 0.0.0.0/0 on TCP 443 (only if pods must call external APIs). If you can, replace with “allow-egress-to-egress-gateway” (preferred) instead of open internet. allow-ingress-from-ingress-controller Allow ingress to app pods only from ingress-nginx (or your ingress namespace)